## Sheet1
ID | User Story Title | User Story Description | Priority | Estimated Effort
US1 | User Registration | As a user, I want to create an account so that I can securely store my financial data. | 10 | 3 Days
US2 | User Login | As a user, I want to log into the system so that I can access my expense records securely. | 10 | 2 Days
US3 | Add Expenses | As a user, I want to add daily expenses so that I can track my spending habits. | 10 | 4 Days
US4 | Edit Expenses | As a user, I want to edit expense records so that I can correct mistakes in my data. | 20 | 2 Days
US5 | Delete Expenses | As a user, I want to delete incorrect expense records so that my financial reports remain accurate. | 20 | 1 Day
US6 | Expense Categorization | As a user, I want to categorize my expenses so that I can better understand my spending patterns. | 20 | 3 Days
US7 | Monthly Budget Setup | As a user, I want to create a monthly budget so that I can control my spending. | 20 | 4 Days
US8 | Budget Alerts | As a user, I want to receive notifications when my spending exceeds my budget so that I can reduce overspending. | 30 | 3 Days
US9 | Monthly Financial Reports | As a user, I want to generate monthly financial reports so that I can analyze my financial performance. | 30 | 5 Days
US10 | Spending Trend Analysis | As a user, I want to analyze spending trends so that I can improve my financial habits. | 30 | 4 Days
US11 | Dashboard Overview | As a user, I want to view a dashboard summary so that I can quickly check my financial status. | 30 | 3 Days
US12 | Responsive Design | As a user, I want the application to work properly on mobile devices so that I can access it anywhere. | 40 | 4 Days
US13 | Secure Password Protection | As a user, I want my account password to be securely protected so that my financial information remains safe. | 10 | 3 Days
US14 | Secure Database Storage | As a user, I want my financial data to be stored securely so that unauthorized users cannot access it. | 10 | 4 Days
US15 | Admin User Management | As an admin, I want to manage user accounts so that the system remains organized and secure. | 50 | 3 Days
US16 | Expense Search Function | As a user, I want to search my expenses so that I can quickly find specific financial records. | 40 | 2 Days
US17 | Expense Filter Function | As a user, I want to filter expenses by category or date so that I can review specific transactions easily. | 40 | 3 Days
US18 | Export Financial Reports | As a user, I want to export my financial reports so that I can save or print them for future reference. | 50 | 4 Days